## Slide 1: Inclusive Senior Education through Virtual U3V
financial conditions
documents
obligatory forms
submission deadlines

## Slide 2: Budget
Budget of the project in summary: 195.935,- EUR
AMBESP Portugal 41.035,- EUR
FMD Italy 53.150,- EUR
RUTIS Portugal 41.955,- EUR
Ostravská univerzita 58.850,- EUR
Reserve 945,- EUR
The reserve was created by moving the final meeting from the Czech Republic to Portugal.
The final meeting will take place during blended mobility.

## Slide 3: RESERVE
Can be used by any partner for:
seniors with specific needs (blended mobility)
to increase the number of seniors for blended mobility
to increase the number of meeting participants
Requirements must be communicated
to the coordinator in advance!

## Slide 4: Budget transfers
move from any chapter up to 20%
increasing chapters Project Management and Implementation and Exceptional Costs is not possible!
increase up to 20% for chapters Transnational Project Meetings, Intelectual Outputs and Learning/Teaching (Blended mobility)
costs for participants with specific needs can be increased without restrictions.

## Slide 5: Budget chapters
Project Management and Implementation
labour costs (staff) for project management and administration
promotion and project information campaign
brochures, teaching materials
websites
Flat-rate, we do not recommend moving funds from this chapter.

## Slide 6
Transnational Project Meetings
contribution for travel and subsistence costs for meeting participants:
100 – 1999 km 575,- EUR/person
> 2000 km 760,- EUR/person
Working relationship between
the organisation and the participant is necessary!

## Slide 7: Intelectual Outputs salaries of O1 - O3 employees according to project applications by country rates:
Czech Republic, Portugal
Manager 164 EUR/day (8 hours)
Technician 102 EUR/day (8 hours)
Adm. support 78 EUR/day (8 hours)
Expert 137 EUR/day (8 hours)
Numbers of days for individual positions and intellectual outputs are listed
in the budgets of each organisation.
Italy
Manager 280 EUR/day (8 hours)
Technician 162 EUR/day (8 hours)
Adm. support 131 EUR/day (8 hours)
Expert 214 EUR/day (8 hours)

## Slide 8: Blended mobility
travel and subsistence costs of seniors
the approved duration of mobility: 7 days
Travel rates by distance
(10 – 99 km = 20 EUR/participant – for seniors from RUTIS,
500 – 1999 km = 275 EUR/participant – for seniors from Italy,
2000 – 2999 km = 360 EUR/participant – for seniors from Czech Republic)
Contrubution to subsistence costs
(accommodation, food, local transport): 55 EUR/participant (only for seniors from
Italy and Czech Republic)

## Slide 9: Exceptional Costs
Costs of services that can not be provided by any of the organisations in the project.
This is not a purchase of computer equipment or office supplies.
In our project only actual costs of translation services and video lessons processing!
75% of real costs will be reimbursed, 25% of costs is participation of the organisation

## Slide 10: Eligible (acceptable) costs
dated during the duration of the project (2.10.2017 – 1.8.2020)
documented by invoice, bill, financial statements, etc.
necessary for the implementation of the project

## Slide 11: Ineligible (unacceptable) costs
dated before or after the project
unreasonable costs
the cost of opening and keeping bank accounts
material or incomplete performance of third parties
VAT, which can be recovered under national regulations

## Slide 12: Documents and forms
Project Management and Implementation
there is no need to report Erasmus
for possible control: the invoices, bills, employment contracts, financial statements from the organisation's account, etc.

## Slide 13: Transnational Project Meetings
attendance list
detailed agenda of meeting
confirmation of attendance for each participant issued by the receiving organisation
employment contract for each participant
tickets and bording pass

## Slide 14
 |  |  | Attendance list - Transnational Project Meeting |  | 
Agreement number: |  |  | 2017-1-CZ01-KA204-035438 |  | 
Project: |  |  | Inclusive Senior Education through Virtual U3A - ISEV |  | 
Activity: |  |  | kick-off meeting |  | 
Place: |  |  | Ostrava, Czech Republic |  | 
 |  | Date (from - to): | 27 - 28 November 2017 |  | 
 | Participant name | Participant email | Sending organisation | Country of the sending organisation | Signature
1 | Zdeňka Telnarová | zdenka.telnarova@osu.cz | Ostravská univerzita | Czech Republic | 
2 |  |  |  |  | 
3 |  |  |  |  | 
4 |  |  |  |  | 
5 |  |  |  |  | 
6 |  |  |  |  | 
7 |  |  |  |  | 
8 |  |  |  |  | 
9 |  |  |  |  | 
10 |  |  |  |  | 
 |  |  |  | ………………………………………………………… | 
 |  |  |  | Zdeňka Telnarová | 
 |  |  |  | Ostravská univerzita | 
 |  |  |  | 28.11.2017 | 

## Slide 15
Confirmation of attendance: Kick-off meeting
Project: Inclusive Senior Education through Virtual U3A - ISEV
Agreement number: 2017-1-CZ01-KA204-035438
Receiving organisation: Ostravská univerzita
Meeting place: Czech Republic, 701 03 Ostrava, ul. 30. dubna 22
We confirm that Mrs. Vera Ribeiro from Associação de Melhoramentos e Bem Estar Social de Pias, address: Portugal, 2240-612 Ferreira do Zêzere, Largo Dr. José Real da Silva Sousa Canêdo, n.° 22, participated in a foreign stay at a transnational project meeting in Ostrava from 27 November to 28 November 2017.
Ostrava, 28 November 2017 ……………………. Zdeňka Telnarová
Ostravská univerzita

## Slide 16: Intelectual Outputs
employment contracts for each person
time sheets – monthly
documenting actual wage payments
(for example accounting report, bank statements)

## Slide 17: DO NOT FORGET:
 |  | TIME SHEET |  |  | 
 | Project: | Inclusive Senior Education through Virtual U3A - ISEV |  | November 2017 | 
 | Agreement number | 2017-1-CZ01-KA204-035438 |  |  | 
 | organisation: | Ostravská univerzita |  |  | 
 | Country: | Czech Republic |  |  | 
 | Name: | Zdeňka Telnarová |  |  | 
Date (e.g. 01/01/15) | Number of working hours | Number of working days | Description of activity | Category | Unit costs per day
 |  | 0 | O3 - | Manager | 164
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
 |  | 0 |  |  | 
Total: | 0 | 0 |  |  | 
 | Signature of employee: |  | Approved (signature): |  | 
 | Date: |  | Date: |  | 
The period of reported work must correspond to the duration of the activities according to the timetable
Describe the activities clearly and comprehensively
Time sheet must be signed by the employee and the project manager (in each partner organisation)

## Slide 18: Create 2 originals of the time sheet: 1 original to the coordinator 1 original to the archive in your organisation for 5 years after the end of the project

## Slide 19: Blended mobility
attendance list
detailed agenda of blended mobility
confirmation of attendance for each senior issued by the receiving organisation
tickets and bording pass

## Slide 20
Confirmation of participation in blended mobility
Project: Inclusive Senior Education through Virtual U3A - ISEV
Agreement number: 2017-1-CZ01-KA204-035438
Receiving organisation:
Associação de Melhoramentos e Bem Estar Social de Pias
Meeting place:
Portugal, 2240-612 Ferreira do Zêzere, Largo Dr. José Real da Silva Sousa Canêdo, n.° 22
We confirm that...........(name of senior – participant of the blended mobility) from ........... (name of the sending organisation, address) participated in a foreign stay at blended mobility in Ferreira do Zêzere from ………… to …………… 2019 (date of the event - no trip).
Ferreira do Zêzere, ……….. …………………….
Vera Ribeiro
AMBESP

## Slide 21: Exceptional Costs
invoice or bill
bank statement or another proof of payment
VAT declaration (We are a registered VAT payer ....)
declaration of compliance of public procurement (according to the valid legislation in each country)
These declarations do not have an obligatory form, they may be contained in
one document signed by the statutory representative.
The original invoice must be archived at least
5 years after the end of the project!

## Slide 22: Monitoring
The Coordinator is required to inform the European Commission about the progress
of the project through the Mobility Tools platform
We need your periodic information about:
ACTIVITIES – send to Zdeňka (zdenka.telnarova@osu.cz)
COSTS – send to Pavla (pavla.janoschova@osu.cz)

## Slide 23: Deadlines
The deadlines for submitting interim reports are set out in the partnership agreement, the coordinator is responsible for the deadline.
Your documents every 3 months, always by the 15th of the following month
1. 10. – 31.12. 2017: no later than 15 January 2018
1.1. – 31.3. 2018: no later than 15 April 2018 etc.
or on request!

## Slide 24: Documents by e-mail
Please, send to Pavla:
employment contracts for each person (project management + intelectual outputs)
time sheets – monthly (intelectual outputs)
documents confirm payment of wages (intelectual outputs)
invoices or bills (exceptional costs), if you have
+ bank statement or another proof of payment
+ VAT declaration + declaration of compliance of public procurement
tickets and bording pass (your trip to Ostrava)
table of drawing of funds (VERY IMPORTANT!)

## Slide 25: Documents by mail
The originals of time-sheets should be sent, please, by mail (from a post office ) every half year.

## Slide 26: Table of drawing of funds
You will find it printed in a folder.
Fill in the actual costs according to the accounting reports - documents each month!
Sums and drawing in percent are calculated automatically. Please do not change formulas.

## Slide 27: Table of drawing of staff costs
You will find it printed in a folder.
Fill in the actual costs according to the accounting reports - documents each month!
Sums are calculated automatically. Please do not change formulas. Only light fields can be filled in - in accordance with the time table.